## Summary
Template | Delivery Department KPI
Period Start (YYYY-MM-DD) | 2026-01-01
Period End (YYYY-MM-DD) | 2026-01-31
Goal Comments
Goal Key | Goal Name | Comment
billability_utilization | Billability & Utilization
delivery_excellence | Delivery Excellence
quality_process | Quality & Process
value_client | Value Add & Client Satisfaction

## Raw Delivery Log
Month / Period
Sr No | Ticket/Task ID | Project/Module | Issue Description | Issue Date | Due Date | Delivery Date | Delivered? (Y/N) | Rework Required? (Y/N) | Rework Count | Escalated? (Y/N) | Escalation Level | Post-Delivery Defect? (Y/N) | Defect Count | Type | Root Cause | Reference Link | FTR Flag | ESC Flag | PDD Flag | Scope Request? (Y/N) | Approved Scope Change? (Y/N) | Milestone? (Y/N) | Milestone On Time? (Y/N) | Formal Change Logged? (Y/N) | Automation Used? (Y/N) | Additional Initiative? (Y/N) | CSAT Score
1 | M0093 | M0093_SharePoint_to_DMP | File Management Issue | 2026-01-29 | 2026-02-03 | 2026-02-02 | Y | N | 0 | Y | None | N | 0 | Bug | Incorrect Mappings in RestClient Step | M0093
2 | 564 | M0098_DMP_to_FoodLink | Scratch Development | 2026-01-23 | 2026-01-30 | 2026-01-30 | Y | Y | 2 | N | None | N | 0 | Bug | Requirement Change | TORIDOLL_INTERNAL-564
3 | 261 | M0025_JNAL_DMPtoBlackLine | DDL for creating internal TB is not for MySQL | 2026-02-04 | 2026-02-06 | 2026-02-06 | Y | N | 0 | N | None | N | 0 | Bug | - | TORIDOLL_INTERNAL-261
4 | 641 | M0025_JNAL_DMPtoBlackLine | Unable to get S3 in bulk | 2026-02-04 | 2026-02-06 | 2026-02-06 | Y | N | 0 | N | None | N | 0 | Bug | - | TORIDOLL_INTERNAL-641
5 | 521 | ngc |  | 2026-02-04 | 2026-02-08 | 2026-02-06 | Y | N | 0 | N | None | Y | 0 | Value Add
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
Total Delivered (Y) |  | Count
First Time Right Count |  | Count
Escalation Count |  | Count
Post-Delivery Defect Count |  | Count
First Time Right (%) |  | %
Escalation Rate (%) |  | %
Post-Delivery Defect Rate (%) |  | %
Total Scope Requests (Proxy) |  | Count
Approved Scope Changes (Proxy) |  | Count
Total Milestones (Proxy) |  | Count
Milestones On-Time (Proxy) |  | Count
Total Projects Delivered |  | Count
Projects On-Time/Budget |  | Count
Rework Count |  | Count
Formal Changes (Proxy) |  | Count
Total Changes (Proxy) |  | Count
Total Projects (Row Count) |  | Count
Automated Projects (Proxy) |  | Count
Additional Initiatives |  | Count
CSAT Total Score (Proxy) |  | Score
CSAT Total Responses (Proxy) |  | Count
Compliant Deliveries (Proxy FTR) |  | Count

## Billability & Utilization
Goal Key | billability_utilization
Goal Name | Billability & Utilization
Description | Ensure optimal utilization of delivery resources and maximize billable contribution.
Goal Comment
Metric Key | Metric Label | Type | Required | Definition | Value | Comment
bu_billable_hours | Billable Hours (Input) | NUMBER | Yes |  | 8
bu_available_hours | Available Hours (Input) | NUMBER | Yes |  | 50
bu_total_working_hours | Total Working Hours (Input) | NUMBER | Yes |  | 120
utilization_rate | Utilization Rate (%) | PERCENT | Auto | Measures the percentage of available working hours that are spent on billable activities.
billability_rate | Billability Rate (%) | PERCENT | Auto | Measures percentage of total working time that is billable to clients.

## Delivery Excellence
Goal Key | delivery_excellence
Goal Name | Delivery Excellence
Description | Ensure projects are delivered on time, within budget, and with high quality.
Goal Comment
Metric Key | Metric Label | Type | Required | Definition | Value | Comment
de_projects_on_time_budget | Projects Delivered On Time & Budget (Input) | NUMBER | Yes
de_total_projects_delivered | Total Projects Delivered (Input) | NUMBER | Yes
de_approved_scope_changes | Approved Scope Changes (Input) | NUMBER | Yes
de_total_scope_requests | Total Scope Change Requests (Input) | NUMBER | Yes
de_deliverables_accepted | Deliverables Accepted Without Rework (Input) | NUMBER | Auto (Raw Sheet)
de_total_deliverables | Total Deliverables (Input) | NUMBER | Auto (Raw Sheet)
de_milestones_on_time | Milestones Completed On Time (Input) | NUMBER | Yes
de_total_milestones | Total Milestones (Input) | NUMBER | Yes
de_escalation_count | Escalation Count (Input) | NUMBER | Auto (Raw Sheet)
de_post_delivery_defects | Post Delivery Defects (Input) | NUMBER | Auto (Raw Sheet)
de_total_deliveries | Total Deliveries (Input) | NUMBER | Auto (Raw Sheet)
on_time_delivery | On-Time & On-Budget Delivery (%) | PERCENT | Auto | Measures percentage of projects delivered on time and within approved budget.
scope_change_control | Scope Change Control Effectiveness (%) | PERCENT | Auto | Measures effectiveness of managing and controlling project scope changes.
first_time_right | First Time Right (%) | PERCENT | Auto | Measures percentage of deliverables accepted by client without requiring rework.
schedule_adherence | Schedule Adherence (%) | PERCENT | Auto | Measures how well project milestones are delivered as per planned schedule.
escalation_rate | Escalation Rate (Count) | NUMBER | Auto | Measures number of client escalations during delivery period.
post_delivery_defect_rate | Post Delivery Defect Rate (%) | PERCENT | Auto | Measures defects reported after delivery completion.

## Quality & Process
Goal Key | quality_process
Goal Name | Quality & Process
Description | Ensure adherence to defined processes and maintain high quality standards.
Goal Comment
Metric Key | Metric Label | Type | Required | Definition | Value | Comment
qp_rework_count | Deliverables Requiring Rework (Input) | NUMBER | Yes
qp_total_deliverables | Total Deliverables (Input) - Quality | NUMBER | Yes
qp_compliant_deliveries | Process Compliant Deliveries (Input) | NUMBER | Yes
qp_total_deliveries | Total Deliveries (Input) - Process | NUMBER | Yes
qp_formal_changes | Formally Managed Changes (Input) | NUMBER | Yes
qp_total_changes | Total Changes (Input) | NUMBER | Yes
qp_automated_projects | Projects Using Automation (Input) | NUMBER | Yes
qp_total_projects | Total Projects (Input) | NUMBER | Yes
delivery_error_rework_rate | Delivery Error / Rework Rate (%) | PERCENT | Auto | Measures percentage of deliverables requiring correction or rework.
process_compliance_rate | Process Compliance Rate (%) | PERCENT | Auto | Measures adherence to defined SOPs and delivery processes.
change_management_adherence | Change Management Adherence (%) | PERCENT | Auto | Measures percentage of changes handled using formal change management process.
automation_adoption | Automation Adoption (%) | PERCENT | Auto | Measures usage of automation in delivery activities.

## Value Add & Client Satisfaction
Goal Key | value_client
Goal Name | Value Add & Client Satisfaction
Description | Deliver additional business value and ensure high client satisfaction.
Goal Comment
Metric Key | Metric Label | Type | Required | Definition | Value | Comment
vc_additional_initiatives | Additional Initiatives Completed (Input) | NUMBER | Yes
vc_total_score | Total Client Ratings Score (Input) | NUMBER | Yes
vc_total_responses | Total Client Responses (Input) | NUMBER | Yes
additional_initiatives_delivered | Additional Initiatives Delivered (Count) | NUMBER | Auto | Measures number of additional value-added initiatives beyond planned delivery.
csat_score | Client Satisfaction Score (CSAT) | NUMBER | Auto | Measures client satisfaction level based on feedback ratings.

## AutoFill Notes
Current Template Raw-Driven AutoFill Sample (No code changes)
Purpose: Fill Raw Delivery Log only; Delivery/Quality/Value metrics auto-fill via formulas.
File source: delivery-department-kpi (3).xlsx
What was kept same
- Existing sheet names and structure are unchanged.
- Existing Delivery/Quality/Value computed formulas remain intact.
What was added for full auto-fill demo
- Proxy helper columns U:AB on Raw Delivery Log.
- Extended summary rows B48:B62 on Raw Delivery Log.
- Input metric cells in Delivery/Quality/Value link to Raw summary cells.
Proxy assumptions (for manager review)
- Scope/FORMAL/Automation/Initiative are derived by helper formulas from existing raw fields.
- CSAT Score uses proxy formula: 5 when Additional Initiative = Y, else blank.
- These can be replaced later with actual explicit raw input columns if approved.