## Raw Delivery Log
SR NO | TICKET/TASK ID | PROJECT/MODULE | ISSUE DESCRIPTION | ISSUE DATE | DUE DATE | DELIVERY DATE | DELIVERED? (Y/N) | REWORK REQUIRED? (Y/N) | REWORK COUNT | ESCALATED? (Y/N) | ESCALATION LEVEL | POST-DELIVERY DEFECT? (Y/N) | SCOPE REQUEST? (Y/N) | APPROVED SCOPE CHANGE? (Y/N) | MILESTONE? (Y/N) | MILESTONE ON TIME? (Y/N) | FORMAL CHANGE LOGGED? (Y/N) | AUTOMATION USED? (Y/N) | ADDITIONAL INITIATIVE? (Y/N) | CSAT SCORE | REFERENCE NAME | REFERENCE URL | REFERENCE LINK
1 | M0093 | M0093_SharePoint_to_DMP | File Management Issue | 2026-01-29 | 2026-02-03 | 2026-02-02 | Y | N | 0 | Y | None | N | N | N | Y | Y | N | Y | Y | 4 | Root Cause Doc | https://example.com/rca-m0093
2 | 564 | M0098_DMP_to_FoodLink | Scratch Development | 2026-01-23 | 2026-01-30 | 2026-01-30 | Y | Y | 2 | N | None | N | Y | N | Y | Y | Y | N | N | 5 | Change Request | https://example.com/cr-564
3 | 261 | M0025_JNAL_DMPToBlackLine | DDL internal TB issue | 2026-02-04 | 2026-02-06 | 2026-02-06 | Y | N | 0 | N | None | N | N | N | Y | Y | N | Y | N | 4 | Tech Notes | https://example.com/tech-261
4 | 641 | M0025_JNAL_DMPToBlackLine | Unable to get S3 in bulk | 2026-02-04 | 2026-02-06 | 2026-02-06 | Y | N | 0 | N | None | N | Y | Y | Y | Y | Y | N | N | 3 | S3 Investigation | https://example.com/s3-641
5 | 521 | ngc | General Support | 2026-02-04 | 2026-02-08 | 2026-02-06 | Y | N | 0 | N | None | Y | N | N | Y | N | N | Y | Y | 5 | Delivery Evidence | https://example.com/deliv-521

## Raw_Summary
metric_key | value | description
de_total_deliverables |  | Total delivered count
de_deliverables_accepted |  | First-time-right delivered count
de_escalation_count |  | Escalated items count
de_post_delivery_defects |  | Post-delivery defects count
de_total_deliveries |  | Mirror of total deliverables
de_total_scope_requests |  | Scope requests count
de_approved_scope_changes |  | Approved scope changes
de_total_milestones |  | Total milestones
de_milestones_on_time |  | Milestones on-time
qp_rework_count |  | Total rework count
qp_total_deliverables |  | Mirror of total deliverables
qp_compliant_deliveries |  | Using first-time-right as compliant
qp_total_deliveries |  | Mirror of total deliveries
qp_total_changes |  | Mirror of total scope requests
qp_formal_changes |  | Formal change records
qp_total_projects |  | Distinct projects
qp_automated_projects |  | Distinct automated projects
vc_additional_initiatives |  | Additional initiatives count
vc_total_score |  | Total CSAT score
vc_total_responses |  | CSAT responses count
ftr_rate_percent |  | First time right %
escalation_rate_percent |  | Escalation %
post_defect_rate_percent |  | Post-delivery defect %

## KPI Auto Fill Preview
metric_key | auto_value_from_raw | goal
de_total_deliverables |  | Delivery Excellence
de_deliverables_accepted |  | Delivery Excellence
de_escalation_count |  | Delivery Excellence
de_post_delivery_defects |  | Delivery Excellence
qp_rework_count |  | Quality & Process
qp_total_deliverables |  | Quality & Process
qp_compliant_deliveries |  | Quality & Process
vc_additional_initiatives |  | Value Add & Client Satisfaction
vc_total_score |  | Value Add & Client Satisfaction
vc_total_responses |  | Value Add & Client Satisfaction

## How_To_Use
How To Use (Approval Sample)
1. Fill ONLY Raw Delivery Log rows.
2. Raw_Summary auto-calculates KPI base values.
3. KPI Auto Fill Preview shows values that your KPI goal sheets can read.
4. Reference Link column shows display text but opens URL target.
5. This file is for manager approval of approach before template/code change.